## Sheet1
work_id | work_description | sanctioned_amount | estimated_cost | recommended_amount | total_expenditure | fund_released | state | district | sector | mp_name | implementing_agency | recommendation_date | sanction_date | expected_completion_date | actual_completion_date | completion_percentage | status | payment_count
TEST_UP_001 | Construction of concrete road with side drainage in Shivpur ward | 1500000 | 1500000 | 1600000 | 1420000 | 1500000 | Uttar Pradesh | Varanasi | Roads, Pathways and Bridges | Shri Narendra Modi | District Rural Development Agency (DRDA) | 2024-02-10 | 2024-03-15 | 2024-11-30 | 2024-11-20 | 100 | COMPLETED | 3
TEST_UP_002 | Construction of link road and paver blocks in rural sector | 6500000 | 6200000 | 6500000 | 7800000 | 6500000 | Uttar Pradesh | Varanasi | Roads, Pathways and Bridges | Shri Narendra Modi | Public Works Department (PWD) | 2023-05-12 | 2023-08-20 | 2024-04-30 |  | 55 | DELAYED | 6
TEST_MH_003 | Installation of community solar RO drinking water purification plant | 1800000 | 1800000 | 1800000 | 0 | 1800000 | Maharashtra | Pune | Drinking Water Facility | Shri Murlidhar Mohol | Zilla Parishad Engineering Division | 2023-01-15 | 2023-03-01 | 2023-09-30 |  | 0 | STALLED | 1
TEST_KA_004 | Construction of two smart classrooms and science laboratory in Government High School | 2200000 | 2150000 | 2200000 | 2100000 | 2200000 | Karnataka | Bengaluru Urban | Education | Shri Tejasvi Surya | Karnataka Rural Infrastructure Development Ltd (KRIDL) | 2024-01-10 | 2024-02-25 | 2024-10-15 | 2024-10-10 | 100 | COMPLETED | 4
TEST_BR_005_A | Construction of community hall and boundary wall at Panchayat Bhawan in Rajgir | 2500000 | 2500000 | 2500000 | 1800000 | 2500000 | Bihar | Nalanda | Community Centre / Halls | Shri Kaushlendra Kumar | Building Construction Department | 2023-09-01 | 2023-11-15 | 2024-07-31 |  | 65 | IN_PROGRESS | 2
TEST_BR_005_B | Construction of community hall with boundary wall near Panchayat Bhawan in Rajgir block | 2450000 | 2450000 | 2500000 | 1200000 | 2450000 | Bihar | Nalanda | Community Centre / Halls | Shri Kaushlendra Kumar | Rural Works Department | 2023-09-20 | 2023-12-05 | 2024-08-30 |  | 45 | IN_PROGRESS | 2
TEST_TN_007 | Procurement and installation of advanced neonatal care equipment at Primary Health Centre | 3500000 | 3500000 | 3500000 | 3450000 | 3500000 | Tamil Nadu | Chennai | Health and Family Welfare | Dr. Kalanidhi Veeraswamy | Tamil Nadu Medical Services Corporation | 2024-03-01 | 2024-04-10 | 2024-09-30 | 2024-09-15 | 100 | COMPLETED | 2
TEST_AP_008 | Construction of public community sanitation complex with solar lighting | 1200000 | 1200000 | 1200000 | 1180000 | 1200000 | Andhra Pradesh | Visakhapatnam | Sanitation and Public Health | Shri M. Sribharat | Greater Visakhapatnam Municipal Corporation | 2024-02-15 | 2024-03-25 | 2024-08-15 | 2024-08-01 | 100 | COMPLETED | 3